Temporal patterns of volatile-mediated plant communication in potato

Phase 2: Experiment Execution Period (March 9 - March 12)

March 9 8:00 AM- Experiment Start

Critical Operation – Spodoptera exigua (Beet Armyworm) Herbivory Treatment:

- Wounding Method:  Introduce 2 third-instar Spodoptera exigua (Lepidoptera: Noctuidae) larvae onto each emitter plant (14 emitter plants × 2 larvae = 28 larvae total). (1on one leaf)Confine larvae using clip bags to restrict feeding to a defined leaf area and prevent larval escape. 56 bags in total.

- Standardization Scheme:

  - Measure the total area of each leaf (photograph and measure using ImageJ software).

  - Record the actual damage area percentage for each plant.

- S. exigua Larval Infestation

  - Allow larvae to feed continuously for 24-48h under controlled conditions. Monitor larvae every 12 h; replace any deceased larvae promptly to maintain constant herbivory pressure throughout the infestation period.

  - Photograph each infested leaf against a standardized scale reference at T1/T3 to track the progression of herbivory. Quantify the percentage of leaf area consumed using ImageJ software (threshold-based area measurement). Record initial and final herbivory levels to confirm that actual damage falls within the target range of 20% of total leaf area per plant, ensuring inter-plant consistency.

  - Remove them before collect the Vocs

  - Control Group:put bags as well.

VOC Collection Schedule:

| Time Point | Date/Time | Collection Duration | Remarks |
| --- | --- | --- | --- |
| T0 | March 9, 10:00 AM | NO Collection | Herbivory infestation begins: third-instar S. exigua larvae introduced |
| T1 | March 10, 10:00 AM | 1-2 hours | 24 h post-infestation , see the condition to decide remove larvae or not. But remove them then collect the vocs |
| T2 | March 10, 5:00 PM | 1-2 hours | 31 h post-infestation |
| T3 | March 11, 10:00 AM | 1-2 hours | 48 h post-infestation. Or remove larvae here |
| T4 | March 11, 5:00 PM | 1-2 hours | 55 h post-infestation |
| T5 | March 12, 10:00 AM | 1-2 hours | 72 h post-infestation |
| T6 | March 12, 5:00 PM | 1-2 hours | 79 h post-infestation |
| T7/R6 | March 13, 5:00 PM | No | Collect damaged leaves |

VOC Collection Detailed Operation:

- Pre-collection Preparation:

  - Prepare bags and SKC adsorption tubes 30 minutes in advance.

  - Label each sample (Cage number, Time point, Treatment type).

- Bagging Operation (1-2 hours per collection):

  - Carefully place the 2 L Nalophan bag over the above-ground part of the Emitter plant.

  - Ensure the bag opening is sealed but do not crush the plant.

  - Connect the SKC adsorption tube and pump; set flow rate to 0.25 L/min.

  - 4 cages share one pump; use a splitter to ensure each channel flow rate is 0.25 L/min.7pumps

- End of Collection:

  - Stop pump operation.

  - Carefully remove the bag.

  - Immediately seal the SKC adsorption tube and place it in a freezer for storage.

- Environmental Monitoring:

  - Record temperature, humidity, and light intensity during each collection.

Receiver Plant Sampling Schedule:

| Receiver Plant | Removal Time | Cumulative Exposure Time | Operation |
| --- | --- | --- | --- |
| R1 | March 11, 10:00 AM (Post T3) | 48 hours | Collect leaves, freeze |
| R2 | March 11, 5:00 PM(T4) | 55 hours | Collect leaves, freeze |
| R3 | March 12, 10:00 AM(T5) | 72 hours | Collect leaves,freeze |
| R4 | March 12, 5:00 PM (T6) | 79 hours | Collect leaves, freeze |
| R5 | March 13, 10:00 AM | 96 hours | Collect leaves,freeze |
| R6 | March 13, 5:00 PM | 103 hours | Collect leaves, freeze/Collect damaged leaves from emitters |

Receiver Plant Sampling Detailed Operation:

- Leaf Collection:

  - Collect 2 fully expanded, undamaged leaves from each Receiver plant.

  - Freeze leaves immediately.

  - Place leaves from each plant into separately labeled bags.

  - Transfer to a -80ºC freezer for long-term storage.

- Plant Measurement:

  - Record plant height and leaf count.

  - Photograph to record the overall status of the plant.